## Scope
Room Number | Room Description | Phase | Two Foot Flood Cut Required | Insulation Inspection Required | Total Wall Length (Total Linear Feet) | Ceiling Height (Feet) | Asbestos | Mold | Existing Flooring Finishes | Floor Restoration Required | Base Replacement | Existing Wall Finishes | Wall Restoration Required | Existing Wall Protection Finishes | Wall Protection Restoration Required | Existing Ceiling Finishes | Ceiling Restoration Required | Millwork | Millwork Restoration Required | Furniture | Furniture to be Removed and Stored Offsite | Comments
First Floor
B104 | C & P Exam Room | 1 | No | Yes | 0 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B105 | ED Exam Room | 1 | No | Yes | 0 | 8.3 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B106 | ED Exam Room | 1 | No | Yes | 47.7 | 7.8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B107 | ED Exam Room | 1 | No | Yes | 42.5 | 8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B108 | ED Exam Room | 1 | No | Yes | 42.5 | 8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B109 | ED Staff Room | 1 | No | Yes | 45.2 | 7.8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B110 | ED Exam Room | 1 | No | Yes | 45.2 | 8.2 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B111 | Toilet Room | 1 | No | Yes | 40.8 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to install new flooring.
B112 | C & P Exam Room | 1 | No | Yes | 49.2 | 8.3 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B112A | C & P Office | 1 | No | Yes | 45 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B115 | Nutrition Office | 3 | No | Yes | 54 | 8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B116 | ED Admin. Officer | 3 | No | Yes | 0 | 8 | Not Sampled | Unknown | Plank Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B117 | HAS Office | 2 | No | Yes | 0 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | No | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B118 | Suicide Prevention Office | 2 | No | Yes | 0 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Paint | No | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B121 | Gallery | 1 | No | Yes | 52.1 | 7.4 | Not Sampled | Unknown | Plank Vinyl | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
C1-9 | Main Corridor at Canteen | 1 | No | Yes | 25 | 7.4 | Not Sampled | Unknown | VCT | No | Yes | Paint | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | No | No
C1-10 | Main Corridor Intersection | 1 | No | Yes | 176.1 | 7.4 | Not Sampled | Unknown | VCT | No | Yes | Paint | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | No | No
C1-11 | MOD F Corridor | 1 | No | Yes | 60.3 | 7.2 | None Detected | Unknown | VCT | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
C1-11A | MOD F Corridor (Near Women's Toilet) | 1 | No | Yes | 30 | 7.3 | Not Sampled | Unknown | Plank Vinyl | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
C1-12 | Main Corridor at Gallery | 2 & 3 | No | Yes | 28 | 7.4 | Not Sampled | Unknown | VCT | No | Yes | Paint | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | No | No
C1-13 | Corridor to MOD E | 1 | No | Yes | 56.3 | 7.4 | None Detected | Unknown | Sheet Vinyl | No | Yes | Paint | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | No | No
Second Floor
B201 | Behavioral Health Office | 1 | Yes | Yes | 45 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B202A | Behavioral Health Office | 1 | Yes | Yes | 42 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | 1 Painted Wall, 3 Wallpaper Walls | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B202B | Behavioral Health Office | 1 | Yes | Yes | 42 | 8 | Not Sampled | Unknown | LVT | Yes | Yes | 2 Painted Walls, 2 Wallpaper Walls | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B202C | Behavioral Health Office | 1 | Yes | Yes | 42 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | 1 Painted Wall, 3 Wallpaper Walls | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B203 | Behavioral Health Office | 1 | Yes | Yes | 41 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B204 | EEO Office | 1 | Yes | Yes | 35.8 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B205A | EEO Office | 1 | Yes | Yes | 57 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B205B | Behavioral Health Office | 1 | Yes | Yes | 48 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B206 | Behavioral Health Office | 1 | Yes | Yes | 52.2 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B207 | Electrical Closet | 1 | Yes | Yes | 24 | 10.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Exposed Ceiling | No | No | No | Yes | Yes
B208 | Behavioral Health Office | 1 | No | Yes | 0 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint and Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | Construction signs on door, no active construction. Decorative molding 2.5' from floor, lower portion of all walls is paint upper portion is wallpaper
B209 | Behavioral Health Office | 1 | No | Yes | 48.3 | 7.9 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B210 | Behavioral Health Office | 1 | No | Yes | 34.7 | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B212 | Behavioral Health Office | 2 | No | Yes | 34.7 | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | One 8" x8" register. Acnhor existing diffuser correctly. Do not use electrical tape
B213 | Behavioral Health Office | 2 | No | Yes | 39.9 | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B214 | Behavioral Health Office | 2 | No | Yes | 41.2 | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B215 | Behavioral Health Office | 2 | No | Yes | 34 | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B216 | Behavioral Health Office | 2 | No | Yes | No | 7.8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B217 | Behavioral Health Office | 3 | No | Yes | 38.5 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B218 | Behavioral Health Office | 3 | No | Yes | 37.7 | 7.1 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B219 | HAC Closet | 1 | No | Yes | 20 | 10.5 | Not Sampled | Unknown | Ceramic Tile | No | Yes | Paint | No | No | No | Exposed Ceiling | No | No | No | No | No
B220 | Behavioral Health Work Room | 1 | No | Yes | 30 | 7.1 | None Detected | Mold May Be Present | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | No | No
B220A | CESATE Office | 1 | No | Yes | 34.4 | 7.8 | Not Sampled | Mold May Be Present | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling and Dry Wall | Yes | No | No | Yes | Yes
B221 | Behavioral Health Conference Room | 1 | No | Yes | 73 | 8.4 | None Detected | Mold May Be Present | Carpet | Yes | Yes | Wallpaper and Paint | Yes | Yes | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B221A | Electrical Closet | 1 | No | Yes | 10 | 10.4 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | No | No | No | Exposed Ceiling | No | No | No | No | No
B222 | FEC Closet | 3 | No | Yes | 10 | 10.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Exposed Ceiling | No | No | No | No | No
B223 | Electrical Closet | 3 | No | Yes | 10 | 10.4 | Not Sampled | Unknown | Ceramic Tile | No | Yes | Paint | No | No | No | Exposed Ceiling | No | No | No | No | No
B224 | Men's Toilet Room | 3 | No | Yes | 35 | 7.8 | Not Sampled | Unknown | Ceramic Tile | No | No | Ceramic Tile and Paint | No | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 2 Urinals, 1 Toilet and 2 Sink Vanity in order to repair Ceramic Tile
B225 | MIRECC Waiting | 3 | No | Yes | 35 | 8 | Not Sampled | Unknown | Vinyl Ceramic Tile | No | Yes | Paint | Yes | No | No | Drywall | Yes | No | No | No | No
B225A | Behavioral Health Office | 3 | No | Yes | 40 | 8 | Not Sampled | Unknown | Wood Plank | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B225B | Behavioral Health Office | 3 | No | Yes | 35.2 | 8 | Not Sampled | Unknown | Wood Plank | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B226 | MIRECC Interview Room | 3 | No | Yes | 33 | 7.8 | Not Sampled | Unknown | VCT | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B227 | MIRECC Interview Room | 3 | No | Yes | 59.7 | 7.9 | Not Sampled | Unknown | VCT | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B228 | MIRECC Open Area | 2 & 3 | No | Yes | 80 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B229 | MIRECC Interview Room | 2 | No | Yes | 48.2 | 7.7 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | Room has a sink. Cover under sink 6.6'
B230 | MIRECC Lab | 2 | No | Yes | 25 | 7.8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B231 | MIRECC Interview Room | 2 | No | Yes | 48 | 7.8 | Not Sampled | Unknown | Wood Plank | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | Room has a sink. Cover under sink 6.6'
B232 | Women's Toilet Room | 2 | No | Yes | 0 | 8 | Not Sampled | Unknown | Ceramic Tile | No | No | Ceramic Tiles | No | No | No | Drop Ceiling | Yes | No | No | No | No
B233 | Behavioral Health Reception | 2 | No | Yes | 43.4 | 7.8 | Not Sampled | Unknown | Wood Plank | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B233A | Behavioral Health Storage | 2 | No | Yes | 30.8 | 8 | Not Sampled | Unknown | Wood Plank | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B238 | Prosthetics Reception Area | 3 | No | Yes | 36.5 | 7.8 | Not Sampled | Mold May Be Present | Wood Plank | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes | Contractor to replace expansion joint
B238A | Prosthetics Staff Room | 2 | No | Yes | 42 | 7.8 | Not Sampled | Mold May Be Present | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B238G | Prosthetics Staff Room | 3 | No | Yes | 0 | 7.8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
C2-10 | Main Corridor at Pharmacy / BH | 1, 2, & 3 | No | Yes | 40 | 8 | 3% Chrysolite (Pink w/multi colors 12x12 ft w/Black and Yellow Mastic, 2% Chrysolite Tan Pipe Thread Sealant | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No | Contractor to replace expansion joint
C2-11 | BH / EEO Corridor | 1 | No | Yes | 41.4 | 8 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C2-12 | Main Corridor at Behavioral Health | 1, 2, & 3 | No | Yes | 126 | 8 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C2-13 | MIRECC Waiting Corridor | 2 & 3 | No | Yes | 210 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling / GWB | Yes | No | No | Yes | Yes
C2-14 | MIRECC Internal Corridor | 2 & 3 | No | Yes | 38.1 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
Third Floor
B304 | Eye Clinic Reception | 1A | No | Yes | 64 | 8 | Not Sampled | Unknown | LVT | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B305 | Eye Clinic Waiting | 1A | Yes | Yes | 89.8 | 7.9 | Not Sampled | Unknown | LVT | Yes | Yes | Paint | Yes | Yes, chair rail | Yes | Drop Ceiling | Yes | No | No | Yes | Yes | Contractor to replace expansion joint.
B306 | Dental Waiting | 1A | Yes | Yes | 75.8 | 7.8 | Not Sampled | Unknown | VCT | Yes | Yes | Wallpaper | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | Yes | Yes
B307 | Dental Reception | 1A | Yes | Yes | 5 | 7.9 | None Detected | Unknown | VCT | Yes | Yes | Wallpaper | Yes | Yes, chair rail | No | Drop Ceiling | Yes | Reception Desk | No | Yes | Yes
B308 | Dental Office | 1 | Yes | Yes | 50 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B309 | Dental Office | 1 | Yes | Yes | 38.8 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B310 | Dental Conference Room | 1 | Yes | Yes | 58.8 | 7.9 | Not Sampled | Mold May Be Present | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B311 | Dental Office | 1 | Yes | Yes | 13.6 | 7.9 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B312 | Dental Office | 1 | Yes | Yes | 46.9 | 7.8 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B313 | HAC Closet | 1 | No | Yes | 14.8 | 7.7 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Sink | No | No | No
B314 | Dental Storage | 1 | No | Yes | 15 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
B315 | Dental Clean Supply / Touchdown | 1 | Yes | Yes | 44.9 | 7.9 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B315A | Dental Storage / Closet | 1 | No | Yes | 27.9 | 7.7 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B316 | Dental X-Ray | 1 | Yes | Yes | 70 | 8.3 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Cabinets, sink with counter, desk | No | Yes | Yes | Lead Walls - see drawing A108.2
B316B | Dental X-Ray Lab | 1 | Yes | Yes | 25 | 8.4 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | x-ray machine attached to wall | No | Yes | Yes | Lead Walls - see drawing A108.2
B316C | Dental X-Ray | 1 | Yes | Yes | 36 | 8.3 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Cabinets | Yes | Yes | Yes | Millwork to be replaced. Old sink to be disposed of. New sink to be provded by VA to be installed in new millwork. Lead Walls - see drawing A108.2
B316D | Dental X-Ray | 1 | No | Yes | 40 | 8.3 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Desk | Yes | Yes | Yes | Lead Walls - see drawing A108.2
B317 | HAS Inpatient Supervisors | 1 | No | Yes | 63.8 | 7.8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B319 | Chaplain Office | 3 | No | Yes | 40.8 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint and Wallpaper | Yes, south wall | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B320 | Chaplain Reception Office | 3 | No | Yes | 17.3 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B321 | Chaplain Office | 3 | No | Yes | 42 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B322 | Chaplain Office | 3 | No | Yes | 44 | 8 | Not Sampled | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B323 | PCS Nurse Manager | 3 | No | Yes | 44 | 8 | None Detected | Unknown | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B324 | Women's Toilet Room | 2 | No | Yes | 52 | 8 | Not Sampled | Unknown | Ceramic Tile | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 2 Toilets, 2 Sinks and toilet partitions in order to repair walls and finishes.
B325 | Men's Toilet Room | 2 | No | Yes | 60 | 8 | Not Sampled | Unknown | Ceramic Tile | No | Yes | Paint and Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Urinal, 2 Toilets, 2 Sinks and toilet partitions in order to repair walls and finishes.
3B168 | Chapel Eucharistic Room | 1 | No | Yes | 39.7 | 7.9 | None Detected | Yes | Carpet | Yes | Yes | Wallpaper | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
3B168A | Chapel Storage Room | 1 | No | Yes | 35 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
3B169A | Chapel Storage Room | 1 | No | Yes | 0 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
3B170 | Chapel Storage Room | 1 | No | Yes | 0 | 8 | None Detected | Yes | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
3B171 | Chapel Foyer | 1 | No | Yes | 25.6 | 8 | Not Sampled | Unknown | LVT | No | Yes | Wallpaper, two tone | Yes | Yes | No | Drop Ceiling | Yes | No | No | Yes | Yes
3B169B | Main Chapel | 1 | No | Yes | 20.8 | 20 | Not Sampled | Unknown | Carpet | No | Yes | Wallpaper, two tone | Yes | Yes | No | Dry Wall | No | No | No | Yes | Yes
3B172/ B325A | Electric Closet | 1 | No | Yes | 26 | 8 | Not Sampled | Yes | Concrete | No | Yes | Paint/Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
B326 | Dental Toilet Room | 3 | Yes | Yes | 0 | 7.8 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | Yes | Sink, toilet | No | No | No | Plumbing removal not required.
B327 | Dental OR | 3 | Yes | Yes | 50.3 | 8.3 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Stainless sink, counters, cabinets | Yes | Yes | Yes | Contractor will remove, store, and reinstall stainless steel millwork. Biomed will need to coodinate any equipment protection/removal for items such as Phillips monitor hanging on the walls, also IT has desktop PC's hanging on the walls.
B328 | Dental Closet | 3 | Yes | Yes | 10 | 8 | Not Sampled | Unknown |  |  | Yes
B329 | Dental Staff Room | 3 | Yes | Yes | 57.1 | 8.3 | None Detected | Unknown | VCT | No | Yes | Paint | No | No | No | Drop Ceiling | No | No | No | Yes | Yes
B330 | Dental Closet | 3 | No | Yes | 30 | 8.7 | Not Sampled | Unknown | VCT | No | Yes | Paint | No | No | No | Drop Ceiling | No | No | No | Pegasus Carts | No
B331 | Dental Closet | 3 | Yes | Yes | 20 | 7.8 | Not Sampled | Unknown | VCT | No | Yes | Paint | No | No | No | Drop Ceiling | No | No | No | Pegasus Carts | No
B332 | Dental Exam Room | 3 | Yes | Yes | 35 | 8.3 | None Detected | Unknown | Sheet Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sinks, countertop | No | Yes | Yes
B333 | Dental Exam Room | 4 | Yes | Yes | 33.3 | 8.3 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sinks, countertop | No | Yes | Yes
B334 | Dental Closet | 4 | Yes | Yes | 16 | 8 | None Detected | Unknown |  |  | Yes | Paint | Yes | No | No | Drop Ceiling | No
B335 | Dental Exam Room | 4 | Yes | Yes | 28.7 | 8.3 | None Detected | Unknown | Sheet Vinyl | No | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sinks, countertop | No | Yes | Yes
B337 | Dental Closet | 4 | No | Yes | 26 | 8.3 | None Detected | Unknown | Sheet Vinyl | No | Yes | Two Tone Paint | Yes | Yes | Yes | Drop Ceiling | No | No | No | Yes | Yes
B352 | Dental OR | 2 | Yes | Yes | 40.8 | 8.3 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | SS, Counters, sink | No | Yes | Yes | Contractor will remove, store, and reinstall stainless steel millwork. Biomed will need to coodinate any equipment protection/removal for items such as Phillips monitor hanging on the walls, and patient lift.
B353 | Dental Oral Surgery Reception | 2 | Yes | Yes | 19.1 | 7.7 | 5% Chrysolite Black Mastic | Unknown | Sheet Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | No | No | No | Yes | Yes
B354 | Dental File Room | 2 | Yes | Yes | 34.2 | 8.3 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B355 | Men's Toilet Room | 1 | No | Yes | 60 | 8 | Not Sampled | Mold May Be Present | Ceramic Tile | Yes | Yes | Paint and Ceramic Tile | Yes | No | No | Drywall | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Urinal, 1 Toilet, 1 Sink and toilet partitions in order to repair walls and finishes. Contractor to replace expansion joint.
B356 | Women's Toilet Room | 1 | No | Yes | 55 | 8 | Not Sampled | Mold May Be Present | Ceramic Tile | Yes | Yes | Paint and Ceramic Tile | Yes | No | No | Drywall | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet, 2 Sinks and toilet partitions in order to repair walls and finishes. Contractor to replace expansion joint.
B357 | Eye Clinic Exam Room | 3 | No | Yes | 36.6 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B358 | Eye Clinic Exam Room | 3 | No | Yes | 41.4 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B359 | Eye Clinic Exam Room | 1 | Yes | Yes | 26.4 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B360 | Eye Clinic Exam Room | 3 | No | Yes | 43.3 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B361 | Eye Clinic Exam Room | 1 | No | Yes | 33.2 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B362 | Eye Clinic Exam Room | 3 | No | Yes | 40.5 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B363 | Eye Clinic Exam Room | 1 | Yes | Yes | 39.4 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B376 | Eye Clinic Staff Room | 2 | No | Yes | 50 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | No | No | No | Yes | Yes
B377 | Eye Clinic Exam Room | 1 | No | Yes | 35.6 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | No | Yes | Yes | Yes | Yes
B378 | Eye Clinic Office | 2 | No | Yes | 36.5 | 8 | Not Sampled | Unknown | LVT Planks | No | Yes | Paint | Yes | No | No | Drop Ceiling | No | No | No | Yes | Yes
B378A | Eye Clinic Office | 2 | No | Yes | 28.3 | 8 | Not Sampled | Unknown | LVT Planks | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B379 | Eye Clinic Procedure Room | 2 | No | Yes | 58 | 8.3 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Hard Ceiling | No | Yes | Yes | Yes | Yes
B380 | Eye Clinic Exam Room | 2 | No | Yes | 34.5 | 8 | None Detected | Unknown | VCT | Yes | Yes | Paint | yes | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B381 | Eye Clinic Exam Room | 1 | Yes | Yes | 40.9 | 8 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | No | Cabinets, sink, counter | Yes | Yes | Yes
B382 | Eye Clinic Exam Room | 2 | Yes | Yes | 36.1 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | No | Cabinets, sink | Yes | Yes | Yes
B383 | Eye Clinic Closet | 2 | No | Yes | 15 | 8 | Not Sampled | Unknown | Quarry Ceramic Tile | No | Yes | Paint | Yes | No | No | Drop Ceiling | No | No | No | Pegasus Carts | No | Contractor to replace expansion joint.
C3-9 | Eye Clinic Waiting Corridor | 1 | No | Yes | 65.9 | 7.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | Yes | No | Drop Ceiling | Yes | No | No | No | No
C3-9A | Eye Clinic Sub-Waiting Area | 1 | No | Yes |  | 8 | Not Sampled | Unknown | VCT | No | Yes | Paint | No | Yes | No | Drop Ceiling | No | No | No | No | No
C3-9B | Eye Clinic Front Internal Corridor |  | No | Yes | 51.3 | 8 | Not Sampled | Unknown | VCT | No | Yes | Paint | No | Yes | No | Drop Ceiling | No | No | No | No | No
C3-9C | Eye Clinic Toilet Room Corridor | 1 | No | Yes | 26 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | Yes | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
C3-9D | Eye Clinic Procedure Room Sub-Waiting Area | 1 & 2 | No | Yes | 45.3 | 8 | None Detected | Unknown | VCT | No | Yes | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | Yes | Yes
C3-9E | Eye Clinic Back Internal Corridor | 1 & 2 | No | Yes | 70.9 | 8 | Not Sampled | Unknown | VCT | No | Yes | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | No | No
C3-10 | Dental External Main Corridor | 1, 1A, & 3 | No | Yes | 93.4 | 7.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | Yes | No | Drop Ceiling | Yes | No | No | No | No
C3-11 | Dental Waiting Room Corridor | 1 | Yes | Yes | 66 | 8 | None Detected | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C3-12 | Chaplain Offices Corridor | 1, 2, & 3 | No | Yes | 71.9 | 7.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | No | Yes | No | Drop Ceiling | Yes | No | No | No | No
C3-13 | Dental Internal Corridor | 1, 2, 3, & 4 | Yes | Yes | 177.3 | 7.3 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint, two tone | No | No | No | Drop Ceiling | No | No | No | No | No
Fourth Floor
B400 | GI / Urology Waiting Room | 1B | No | Yes | 90 | 8 | Not Sampled | Unknown | LVT | Yes | Yes | Wallpaper | Yes | Yes, Chair Rail | Yes | Drop Ceiling | Yes | No | No | Yes | Yes | Contractor to replace expansion joint.
B400A | GI / Urology Unisex Toilet | 1B | No | Yes | 34 | 8 | Not Sampled | Unknown | Ceramic Tile | Yes | Yes | Paint and Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to repair Ceramic Tile
B400B | GI / Urology Unisex Toilet | 1B | No | Yes | 34 | 8 | Not Sampled | Unknown | Ceramic Tile | Yes | Yes | Paint and Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to repair Ceramic Tile
B401 | GI / Urology Reception Area | 1 | Yes | Yes | 52 | 8 | Not Sampled | Mold May Be Present | LVT | Yes | Yes | Paint and Wallpaper | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | Yes | Yes | Millwork will be replaced to match existing. Refer to drawings.
B402 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | Yes | Yes | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B403 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | Yes | Yes | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B404 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | Yes | Yes | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B405 | Work Room | 1 | No | Yes | 26 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B406 | Urology Equipment Room (positive space) | 1 | Yes | Yes | 38 | 8 | Not Sampled | Unknown | Sheet Vinyl | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
B407 | Urology Cystology Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | Sheet Vinyl | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B407A | Urology Cystology Toilet | 1 | No | Yes | 25 | 8 | Not Sampled | Unknown | Ceramic Tile | Yes | Yes | Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to repair Ceramic Tile
B408 | Urology HAC Closet | 1 | No | Yes | 44 | 8 | Not Sampled | Unknown | Concrete | No | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
B409 | Urology Toilet Room | 1 | Yes | Yes | 25 | 8 | Not Sampled | Unknown | Ceramic Tile | Yes | Yes | Ceramic Tile | Yes | No | No | Drop Ceiling | Yes | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to repair Ceramic Tile
B409A | Closet (Linen) | 1 | No | Yes | 6 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings.
B410 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B411 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B412 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B413 | Urology Exam Room | 1 | Yes | Yes | 44 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | No | No | Replace Millwork. Refer to drawings. Contractor to remove, store, clean and reinstall 1 sink in millwork.
B414 | Urology Staff Room | 1 | Yes | Yes | 36 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | Yes | Yes | Yes
B415 | Soiled Utility Room | 1 | Yes | Yes | 36 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | No | No
B416 | (4) GI Nursing Staff | 1 | Yes | Yes | 70 | 8 | Not Sampled | Yes | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B418 | GI Chief | 1C | No | Yes | 44 | 8.4 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B419 | Home Oxygen Staff | 1C | No | Yes | 42 | 8.5 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B420 | Nursing | 1C | No | Yes | 42 | 8.6 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B421 | Nursing | 1C | No | Yes | 42 | 8.7 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B422 | GI Provider Office | 1C | No | Yes | 42 | 8.3 | 4% Chrysolite Black Mastic Under Carpet | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B423 | Nursing | 4 | No | Yes | 40 | 8.7 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B424 | Pulmonary Chief | 4 | No | Yes | 42 | 8.6 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B425 | GI Provider Office | 4 | No | Yes | 44 | 8.6 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B426 | GI Staff Office | 4 | No | Yes | 42 | 8.6 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B427 | Electric Closet | 4 | No | Yes | 8 | 10.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Exposed Ceiling | No | No | No | No | No
B428 | GI Staff Office | 4 | No | Yes | 52 | 8.6 | Not Sampled | Unknown | Carpet | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B429 | Home Oxygen Exam Room | 4 | No | Yes | 52 | 8.7 | Not Sampled | Unknown | LVT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B430 | GI Provider Office | 4 | No | Yes | 60 | 8.7 | Not Sampled | Unknown | LVT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | No | No | Yes | Yes
B431 | Electric Closet | 2 | No | Yes | 8 | 10.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Exposed Ceiling | No | No | No | No | No
B432 | Electric Closet | 2 | No | Yes | 15 | 10.5 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | No | No | Exposed Ceiling | No | No | No | No | No
B433 | GI Triage Room | 2 | No | Yes | 54 | 8.7 | Not Sampled | Unknown | LVT | Yes | Yes | Paint | Yes | No | No | Drop Ceiling | Yes | Yes | No | Yes | Yes
B434 | GI Exam Room | 2 | No | Yes | 56 | 8.5 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | Yes | Yes
B435 | GI Exam Room | 2 | No | Yes | 55 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | Yes | Yes
B436 | HAC Closet | 2 | No | Yes | 24 | 8 | Not Sampled | Unknown | Ceramic Tile | No | No | Paint and Tile | No | No | No | Drop Ceiling | No | Yes | No | No | No
B437 | GI Exam Room | 2 | No | Yes | 32 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | Yes | Yes
B438 | GI Exam Room | 2 | No | Yes | 56 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | Yes | No | Drop Ceiling | No | Yes | No | Yes | Yes
B439 | Home Oxygen O2 Storage Room | 2 | No | Yes | 16 | 8 | Not Sampled | Unknown | VCT | No | No | Paint | No | No | No | Drop Ceiling | No | No | No | No | No
B450 | GI Med Nook | 3 | No | Yes | 8 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | Yes | Paint | Yes | No | No | Drop Ceiling | No | No | No | No | No
B451 | GI Exam Room | 3 | No | Yes | 44 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | No | No | Drop Ceiling | No | Yes | No | Yes | Yes
B452 | GI Exam Room | 3 | No | Yes | 20 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | No | No | Drop Ceiling | No | Yes | No | Yes | Yes
B453 | IT Closet | 3 | No | Yes | 15 | 8 | Not Sampled | Unknown | VCT | No | No | Paint | No | No | No | Drop Ceiling | No | No | No | No | No
B454 | GI Exam Room | 3 | No | Yes | 44 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | No | No | Drop Ceiling | No | Yes | No | Yes | Yes
B455 | GI Exam Room | 3 | No | Yes | 44 | 8 | Not Sampled | Unknown | Sheet Vinyl | No | No | Paint | No | No | No | Drop Ceiling | No | Yes | No | Yes | Yes
B456 | GI Toilet Room | 3 | No | Yes | 15 | 8 | Not Sampled | Unknown | Ceramic Tile | No | No | Paint | Yes | No | No | Drop Ceiling | No | No | No | No | No | Contractor will remove, store, and reinstall 1 Toilet and 1 Sink in order to repair Ceramic Tile
B457 | Pulmonary Waiting Room | 1A | No | Yes | 64 | 7.6 | Not Sampled | Unknown | LVT | Yes | Yes | Paint and Wallpaper | Yes | Yes | Yes | Drop Ceiling | Yes | No | No | Yes | Yes | Contractor to replace expansion joint.
C4-10 | GI /Pulmonary Waiting Area Corridor | 1A & 1B | No | Yes | 60 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No | Contractor to replace expansion joint.
C4-10A | Urology/GI Intersecting Corridor | 1, 1A, 2, & 4 | No | Yes | 40 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C4-11 | Urology Corridor | 1 | No | Yes | 40 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C4-12 | Admin Area Corridor | 1C & 4 | No | Yes | 100 | 8 | Not Sampled | Unknown | VCT | Yes | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No
C4-13 | GI Exam Corridor | 1A, 2 & 3 | No | Yes | 100 | 8 | Not Sampled | Unknown | VCT | No | Yes | Paint | Yes | Yes | No | Drop Ceiling | Yes | No | No | No | No

## Activations
Room Number | Room Description | Scott Towel Dispenser | Hand Soap Dispenser | Hand Sanitizer Dispenser | Wipe Dispenser | Glove Box Holder | Toilet Seat Cover Dispenser | Toilet Paper Dispenser | Sanitatry Napkin Dispener | Baby Changing Table | Sharps Dispenser | Curtain Track | Wall Otoscope/BP | Activiations
First Floor
B104 | C & P Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B105 | ED Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B106 | ED Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B107 | ED Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B108 | ED Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B109 | ED Staff Room
B110 | ED Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C
B111 | Toilet Room | C | C | C | C |  | C | C | [5 empty] | Contractor remove existing and install new papertowel dispenser, hand soap, hand sanitizer, TP dispenser and Disposable seat cover holder.
B112 | C & P Exam Room | C | C | C | C | C | C | C |  |  | C, S, C | C, S, C |  | Contractor remove existing and install new papertowel dispenser, hand soap, hand sanitizer, curtain track and glove box dispenser.
B112A | C & P Office
B115 | Nutrition Office
B116 | ED Admin. Officer
B117 | HAS Office
B118 | Suicide Prevention Office
B121 | Gallery
C1-9 | Main Corridor at Canteen
C1-10 | Main Corridor Intersection
C1-11 | MOD F Corridor
C1-11A | MOD F Corridor (Near Women's Toilet)
C1-12 | Main Corridor at Gallery
C1-13 | Corridor to MOD E
Second Floor
B201 | Behavioral Health Office
B202A | Behavioral Health Office
B202B | Behavioral Health Office
B202C | Behavioral Health Office
B203 | Behavioral Health Office
B204 | EEO Office
B205A | EEO Office
B205B | Behavioral Health Office
B206 | Behavioral Health Office
B207 | Electrical Closet
B208 | Behavioral Health Office
B209 | Behavioral Health Office
B210 | Behavioral Health Office
B212 | Behavioral Health Office
B213 | Behavioral Health Office
B214 | Behavioral Health Office
B215 | Behavioral Health Office
B216 | Behavioral Health Office
B217 | Behavioral Health Office
B218 | Behavioral Health Office
B219 | HAC Closet
B220 | Behavioral Health Work Room
B220A | CESATE Office
B221 | Behavioral Health Conference Room | [12 empty] | Activations: Contractor remove, store and re-install TVs/TV mounts, speakers.
B221A | Electrical Closet
B222 | FEC Closet
B223 | Electrical Closet
B224 | Men's Toilet Room | C | C | C | C |  | C | C
B225 | MIRECC Waiting
B225A | Behavioral Health Office
B225B | Behavioral Health Office
B226 | MIRECC Interview Room
B227 | MIRECC Interview Room
B228 | MIRECC Open Area
B229 | MIRECC Interview Room
B230 | MIRECC Lab
B231 | MIRECC Interview Room
B232 | Women's Toilet Room | C | C | C | C |  | C | C | C | C, S, C
B233 | Behavioral Health Reception
B233A | Behavioral Health Storage
B238 | Prosthetics Reception Area | [12 empty] | Activations: Contractor remove, store and re-install TVs/TV mounts
B238A | Prosthetics Staff Room | [12 empty] | Replace 7 ceiling tiles | <<<< | Ceiling Restoration Required in this Room Already
B238G | Prosthetics Staff Room
C2-10 | Main Corridor at Pharmacy / BH
C2-11 | BH / EEO Corridor
C2-12 | Main Corridor at Behavioral Health
C2-13 | MIRECC Waiting Corridor
C2-14 | MIRECC Internal Corridor
Third Floor
B304 | Eye Clinic Reception
B305 | Eye Clinic Waiting | [12 empty] | Activations: Remove all TVs/TV mounts, store and re-install.
B306 | Dental Waiting | [12 empty] | Activations: Remove all TVs/TV mounts, store and re-install.
B307 | Dental Reception
B308 | Dental Office
B309 | Dental Office
B310 | Dental Conference Room |  |  | C | C | [8 empty] | Activations: Remove, all TVs/TV mounts & store, wipe dispenser and hand sanitizer dispenser, and re-install.
B311 | Dental Office
B312 | Dental Office
B313 | HAC Closet
B314 | Dental Storage
B315 | Dental Clean Supply / Touchdown
B315A | Dental Storage / Closet
B316 | Dental X-Ray | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: contractor remove and re-install paper towel dispenser, hand santizer dispenser, wipe dispenser, hand soap dispenser, and glove box holder.
B316B | Dental X-Ray Lab | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: contractor remove and re-install paper towel dispenser, hand santizer dispenser, wipe dispenser, hand soap dispenser, and glove box holder.
B316C | Dental X-Ray
B316D | Dental X-Ray
B317 | HAS Inpatient Supervisors
B319 | Chaplain Office
B320 | Chaplain Reception Office |  |  | C | [9 empty] | Activations: contractor remove and re-install hand santizer.
B321 | Chaplain Office
B322 | Chaplain Office
B323 | PCS Nurse Manager
B324 | Women's Toilet Room | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install multiple papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser, and recessed trash can.
B325 | Men's Toilet Room | C | C | C | C |  | C | C
3B168 | Chapel Eucharistic Room
3B168A | Chapel Storage Room
3B169A | Chapel Storage Room
3B170 | Chapel Storage Room
3B171 | Chapel Foyer
3B169B | Main Chapel
3B172 | Electric Closet
B326 | Dental Toilet Room | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, TP dispenser, seat cover dispenser holder, Aero West dispenser, and recessed trash can.
B327 | Dental OR | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install multiple paper towel dispers, hand soap dispensers, wipe holders, Hand sanitizer dispsensers, clocks, patient curtain track, sharps container and otoscope wall unit.
B328 | Dental Closet
B329 | Dental Staff Room
B330 | Dental Closet
B331 | Dental Closet
B332 | Dental Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, and sharps containers and glove box dispenser.
B333 | Dental Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, and sharps containers and glove box dispenser.
B334 | Dental Closet
B335 | Dental Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, and sharps containers and glove box dispenser.
B336 | Dental Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, and sharps containers and glove box dispenser.
B337 | Dental Closet
B352 | Dental OR | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track and glove box dispenser.
B353 | Dental Oral Surgery Reception
B354 | Dental File Room
B355 | Men's Toilet Room | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, TP dispenser, seat cover dispenser holder, Aero West dispenser, and recessed trash can.
B356 | Women's Toilet Room | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install multiple papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser, and recessed trash can.
B357 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, and glove box dispenser.
B358 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractore remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B359 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B360 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B361 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B362 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B363 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B376 | Eye Clinic Staff Room
B377 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B378 | Eye Clinic Office
B378A | Eye Clinic Office
B379 | Eye Clinic Procedure Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B380 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B381 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B382 | Eye Clinic Exam Room | C | C | C | C | C |  |  |  |  | C, S, C |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, sharps container and glove box dispenser.
B383 | Eye Clinic Closet
C3-9 | Eye Clinic Waiting Corridor
C3-9A | Eye Clinic Sub-Waiting Area
C3-9B | Eye Clinic Front Internal Corridor
C3-9C | Eye Clinic Toilet Room Corridor | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, glove box dispenser, TP dispenser and seat cover dispenser holder.
C3-9D | Eye Clinic Procedure Room Sub-Waiting Area |  |  | C
C3-9E | Eye Clinic Back Internal Corridor |  |  | C
C3-10 | Dental External Main Corridor |  |  | C
C3-11 | Dental Waiting Room Corridor
C3-12 | Chaplain Offices Corridor
C3-13 | Dental Internal Corridor |  |  | C
Fourth Floor
B400 | GI / Urology Waiting Room | [12 empty] | Activatons: Remove all TVs/TV mounts and re-install.
B400A | GI / Urology Unisex Toilet | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser and recessed trash can.
B400B | GI / Urology Unisex Toilet | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, and seat cover dispenser holder.
B401 | GI / Urology Reception Area
B402 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B403 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B404 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B405 | Work Room | [12 empty] | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, and fridge. Panic button is on the wall.
B406 | Urology Equipment Room (positive space)
B407 | Urology Cystology Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser, clock and glove box dispenser.
B407A | Urology Cystology Toilet | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser and recessed trash can.
B408 | Urology HAC Closet
B409 | Urology Toilet Room | C | C | C | C |  | C | C | C | C, S, C |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser and recessed trash can.
B409A | Closet (Linen)
B410 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B411 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B412 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B413 | Urology Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B414 | Urology Staff Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, and glove box dispenser.
B415 | Soiled Utility Room
B416 | (4) GI Nursing Staff
B418 | GI Chief
B419 | Home Oxygen Staff
B420 | Nursing
B421 | Nursing
B422 | GI Provider Office
B423 | Nursing
B424 | Pulmonary Chief
B425 | GI Provider Office
B426 | GI Staff Office
B427 | Electric Closet
B428 | GI Staff Office
B429 | Home Oxygen Exam Room | C | C | C | C | C | [7 empty] | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, and sharps dispenser.
B430 | GI Provider Office
B431 | Electric Closet
B432 | Electric Closet
B433 | GI Triage Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, sharps container, wipes dispenser and glove box dispenser.
B434 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B435 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B436 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B437 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B438 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B439 | Home Oxygen O2 Storage Room
B450 | GI Med Nook
B451 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B452 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track and glove box dispenser.
B453 | IT Closet
B454 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B455 | GI Exam Room | C | C | C | C | C |  |  |  |  | C, S, C | C, S, C | C, B, C | Activations: Contractor remove and re-install papertowel dispenser, hand soap dispenser, hand sanitizer dispenser, curtain track, otoscope/bp wall unit and glove box dispenser.
B456 | GI Toilet Room | C | C | C | C |  | C | C | C |  |  |  |  | Activations: Contractor remove and re-install papertowel dispenser, hand soap, hand sanitizer dispenser, sanitary dispesner, TP dispenser, seat cover dispenser holder, baby changing table, Aero West dispenser, nurse call and recessed trash can.
B457 | Pulmonary Waiting Room | [12 empty] | Activatons: Remove all TVs/TV mounts, store and re-install.
C4-10 | GI /Pulmonary Waiting Area Corridor
C4-10A | Urology/GI Intersecting Corridor
C4-11 | Urology Corridor |  |  | C
C4-12 | Admin Area Corridor
C4-13 | GI Exam Corridor
|  | eMotion Towel Dispenser | Hand Soap Dispenser | Hand Sanitizer Dispenser | Wipe Dispenser | Glove Box Holder | Toilet Seat Cover Dispenser | Toilet Paper Dispenser | Sanitatry Napkin Dispener | Baby Changing Table | Sharps Dispenser | Curtain Track | Wall Otoscope/BP
C= Contractor
S= Contractor Store
B=Biomed to Store
|  | 61 | 61 | 68 | 62 | 47 | 21 | 21 | 11 | 10 | 46 | 28 | 12