## Q and A
4 | Subject: | Existing underground storm water system | Another bidder, Another company, 03.25.2024 9:12 AM
| Question: | Please provide details on the existing pipe. For example is the existing pipe perforated?
| Response: | The existing pipe is corrugated galvanized in good condition. It is not perforated.
5 | Subject: | Previously asked questions | Another bidder, Another company, 03.26.2024 8:28 AM
| Question: | Are questions asked in the previous solicitation still applicable to this solicitation?
| Response: | Yes. The project scope has not changed and an addendum will be issued with all clarifications.
7 | Subject: | Louver free area | Another bidder, Another company, 04.03.2024 2:33 PM
| Question: | 08 90 00-2.4, 4. Louver Performance Ratings: a. Free Area: Not less than 8 sq. ft. for 48-inch- (1220-mm-) wide by 48-inch-(1220-mm-) high louver. Most Manufacturers are averaging 6.8 free area for 5" louver including Greenheck. Please advise.
| Response: | 3'x3' louvers are indicated for the salt barn building. The associated manufacturer rating for this size and configuration is acceptable.
9 | Subject: | SIPP Pipe Lining | Another bidder, Another company, 04.03.2024 4:19 PM
| Question: | We would like to submit a substitution request for the SIPP Pipe Lining product on this project. Per the Project Manual, product substitutions are to be submitted in accordance with spec section 012513. We could not find that spec section in the Project Manual. Could it be provided or clarification given on how to submit a product substitution request?
| Response: | Please submit a product to the architect for consideration and it may be added to the approved manufacturer list.
12 | Subject: | Dumpsters | Another bidder, Another company, 04.04.2024 4:07 PM
| Question: | Will each prime be responsible for their own dumpsters/trash removal?
| Response: | Yes.
15 | Subject: | Substitutions | Another bidder, Another company, 04.04.2024 4:13 PM
| Question: | Will Substitutions be permitted after the award of the contract?
| Response: | Contractor may submit substitutions for review but there is no guarantee they will be approved.
20 | Subject: | Existing Underground Stormwater System | Another bidder, Another company, 04.05.2024 2:21 PM
| Question: | Sheet C4 indicates "contractor shall verify the extents of the underground stormwater system prior to earth moving activities". Please provide details and information on what is required for this in order to determine a cost. Can an allowance for all bidders to include be an option for this work?
| Response: | Field verification of existing conditions is the contractor's responsibility. Allowances are not permitted.
22 | Subject: | Vinyl Windows | Timothy Hess, RLS Construction Group, 04.05.2024 4:10 PM
| Question: | Drawing A3.10 references Vinyl Double Hung Windows, however, no specifications are provided. Please advise regarding desired design specifications for these windows.
| Response: | Jeld Wen, Pella, American Craftsman, Simonton, Andersen are acceptable manufacturers per PennDOT specification.
24 | Subject: | Room Finish Schedule | Another bidder, Another company, 04.08.2024 1:37 PM
| Question: | Can you please provide a room finish schedule so we know what finishes to provide and where.
| Response: | The only finishes specified are FRP panel walls, painted GWB ceilings and VCT floors. These finishes are provided throughout the PSB.
25 | Subject: | Interior Wall Sheathing | Another bidder, Another company, 04.08.2024 1:45 PM
| Question: | Is the interior of the personal building being sheathed with osb or gyp? Detail 6 on A3.10 is calling for frp on osb but the picture description looks like gyp. Please clarify.
| Response: | OSB with FRP panel as noted.
26 | Subject: | Frp | Another bidder, Another company, 04.08.2024 1:47 PM
| Question: | Do all the interior walls get covered with frp or just around the openings?
| Response: | All walls.
27 | Subject: | Metal Roofing Panel | Another bidder, Another company, 04.09.2024 8:32 AM
| Question: | What width of roofing panel is required for this project?
| Response: | Panel size, configuration and anchorage shall be determined by manufacturer to comply with stated design and wind uplift criteria.
28 | Subject: | Tpo Roofing System | Another bidder, Another company, 04.09.2024 8:45 AM
| Question: | Please confirm TPO roofing is not apart of this project as mentioned in the 076000 spec.
| Response: | There is no TPO on this project.
29 | Subject: | Vinyl Siding | Another bidder, Another company, 04.09.2024 9:06 AM
| Question: | Please confirm fluid applied weather barriers and nail base insulation is not required on this project as mentioned in spec section 074633.
| Response: | Not required.